## User guide
2017-02-13

	0. Overview
	This spreadsheet is designed to track small projects performed by a small team.
	It is loosely based on SCRUM method, allowing to define and track sprints containing tasks extracted from a backlog.

	Values are to be provided for yellow cells only.

	1. Initialization
	First, populate backlog with known required features.
	For every feature, list (technical) tasks that will have to be performed. One unique id (task id) must be provided for each task.
	Provide an estimate for every task (in person x day). Set revised effort to the same value than estimated effort.

	2. Create a sprint
	Then create a sprint. Reuse the existing predefined sprint sheets.
	To add a third, fourth, etc. sprint, copy/paste the second sprint sheet.
	Note: the second sprint sheet is different from the first one, in order to allow carrying on not ended tasks from previous sprint.
	Consequently, when creating a new sprint sheet, be sure to copy it from the second sprint sheet.
	Set sprint start date.
	Populate the task list, by adding task ids selected from backlog. Task descriptions and revised efforts will be automatically copied.
	Set your availability for every team member (in days).
	If a task from a previous sprint has not been closed (remaining effort > 0), inserting it again into the newly created sprint will take into account current effort from previous sprint.
	To support this, tab names must not contain characters other than letters or figures.

	3. Project tracking
	At the end of every week, report effort spent on related task(s).
	If current effort exceeds estimated effort, set revised effort to a new (greater) value, in backlog sheet.
	When a task is closed with less effort than initially estimated, this lower effort value can be recorded in the revised effort as well.
	At the end of the sprint, you can compare your initial estimate to the revised one.

	Figures for a given week relate to the work planned/performed until the end of the week.

	History
	2017-02-13	Week number for diagram X-axis.
		Corrected effort inheritance from previous sprint.
	2017-01-06	In newly created sprint, current effort is inherited from previous sprint.

## Backlog
2017-02-13

	Feature	Task id	Task	Estimated effort	Revised effort	Sprint		Comment
	Feature 1 description	1000
		1001	Feature 1 task 1 description	1,0	1,0	1
		1002	Feature 1 task 2 description	1,0	1,0	1
		1003	Feature 1 task 3 description	1,0	0,5	1
		1004	Feature 1 task 4 description	1,0	10,0	2		Highly incorrect estimate - started in sprint 1, carried on in sprint 2
	Feature 2 description	2000
		2001	Feature 2 task 1 description	7,0	11,0	1
		2002	Feature 2 task 2 description	5,0	15,0	1
		2003	Feature 2 task 3 description	5,0	22,0	2
		2004	Feature 2 task 5 description	10,0	10,0	2
		2005	Feature 2 task 6 description	1,0	1,0	2
		2006	Feature 2 task 7 description	4,0	4,0	2
	Feature 3 description	3000
		3001	Feature 3 task 1 description	0,5	0,5	2
		3002	Feature 3 task 2 description	2,0	2,0	2
		3003	Feature 3 task 3 description	2,0	2,0
		3004	Feature 3 task 4 description	4,0	4,0
		3005	Feature 3 task 5 description	0,5	0,5
		3006	Feature 3 task 6 description	0,5	0,5

	TOTAL			45,5	85,0

## Sprint01
2017-02-13

		Sprint 1					Sprint calendars

		Start date	2016-11-28					AA					BB					XX					XX					XX

					2016-11-28	2016-12-05	2016-12-12	2016-12-19	2016-12-26	2017-01-02	2017-01-09	2017-01-16		2016-11-28	2016-12-05	2016-12-12	2016-12-19	2016-12-26	2017-01-02	2017-01-09	2017-01-16		2016-11-28	2016-12-05	2016-12-12	2016-12-19	2016-12-26	2017-01-02	2017-01-09	2017-01-16		2016-11-28	2016-12-05	2016-12-12	2016-12-19	2016-12-26	2017-01-02	2017-01-09	2017-01-16		2016-11-28	2016-12-05	2016-12-12	2016-12-19	2016-12-26	2017-01-02	2017-01-09	2017-01-16
	Task id	Task	Revised effort	Current effort	Remaining effort	47	48	49	50	51	52	1	2	3		48	49	50	51	52	1	2	3		48	49	50	51	52	1	2	3		48	49	50	51	52	1	2	3		48	49	50	51	52	1	2	3
	1001	Feature 1 task 1 description	1	1	0		1,0
	1002	Feature 1 task 2 description	1	1	0					1,0
	1003	Feature 1 task 3 description	0,5	0,5	0		0,5
	1004	Feature 1 task 4 description	10	0,5	9,5					0,5
	2001	Feature 2 task 1 description	11	11	0					3,0	3,0			3,0	2,0
	2002	Feature 2 task 2 description	15	15	0			3,0	4,0	2,0	2,0	4,0

			38,5	29	9,5

					availability		3,0	4,0	4,0	3,0	2,0	5,0	5,0	5,0		4,0	4,0	3,0	0,0	0,0	3,0	3,0	3,0		0,0	0,0	0,0	0,0	0,0	0,0	0,0	0,0		0,0	0,0	0,0	0,0	0,0	0,0	0,0	0,0		0,0	0,0	0,0	0,0	0,0	0,0	0,0	0,0
					current		1,5	3,0	4,0	2,0	2,0	4,0	0,0	0,0		1,5	3,0	3,0	0,0	0,0	3,0	2,0	0,0		0,0	0,0	0,0	0,0	0,0	0,0	0,0	0,0		0,0	0,0	0,0	0,0	0,0	0,0	0,0	0,0		0,0	0,0	0,0	0,0	0,0	0,0	0,0	0,0

					total avail.	51	7,0	8,0	7,0	3,0	2,0	8,0	8,0	8,0
					total current	29	3,0	6,0	7,0	2,0	2,0	7,0	2,0	0,0
					week	47	48	49	50	51	52	1	2	3
					remaining	38,5	35,5	29,5	22,5	20,5	18,5	11,5	9,5	9,5
					ideal rem.	38,5	31,5	23,5	16,5	13,5	11,5	3,5	0,0	0,0

## Sprint02
2017-02-13

		Sprint 2					Sprint calendars

		Start date	2017-01-16					AA					BB					XX					XX					XX

					2017-01-16	2017-01-23	2017-01-30	2017-02-06	2017-02-13	2017-02-20	2017-02-27	2017-03-06		2017-01-16	2017-01-23	2017-01-30	2017-02-06	2017-02-13	2017-02-20	2017-02-27	2017-03-06		2017-01-16	2017-01-23	2017-01-30	2017-02-06	2017-02-13	2017-02-20	2017-02-27	2017-03-06		2017-01-16	2017-01-23	2017-01-30	2017-02-06	2017-02-13	2017-02-20	2017-02-27	2017-03-06		2017-01-16	2017-01-23	2017-01-30	2017-02-06	2017-02-13	2017-02-20	2017-02-27	2017-03-06
	Task id	Task	Revised effort	Current effort	Remaining effort	2	3	4	5	6	7	8	9	10		3	4	5	6	7	8	9	10		3	4	5	6	7	8	9	10		3	4	5	6	7	8	9	10		3	4	5	6	7	8	9	10
	1004	Feature 1 task 4 description	10	10	0					3,0	3,0	3,5
	2003	Feature 2 task 3 description	22	22	0		4,0	4,0	4,0	3,0	3,0		4,0
	2004	Feature 2 task 5 description	10	10	0					3,0	4,0		3,0
	2005	Feature 2 task 6 description	1	1	0					1,0
	2006	Feature 2 task 7 description	4	4	0					4,0

			47	47	0

					availability		4,0	4,0	4,0	3,0	4,0	0,0	4,0	4,0		3,0	3,0	4,0	3,0	4,0	0,0	4,0	4,0		0,0	0,0	0,0	0,0	0,0	0,0	0,0	0,0		0,0	0,0	0,0	0,0	0,0	0,0	0,0	0,0		0,0	0,0	0,0	0,0	0,0	0,0	0,0	0,0
					current		4,0	4,0	4,0	3,0	3,0	0,0	4,0	1,0		3,0	3,0	3,5	3,0	4,0	0,0	3,0	4,0		0,0	0,0	0,0	0,0	0,0	0,0	0,0	0,0		0,0	0,0	0,0	0,0	0,0	0,0	0,0	0,0		0,0	0,0	0,0	0,0	0,0	0,0	0,0	0,0

					total avail.	52	7,0	7,0	8,0	6,0	8,0	0,0	8,0	8,0
					total current	46,5	7,0	7,0	7,5	6,0	7,0	0,0	7,0	5,0
					week	2	3	4	5	6	7	8	9	10
					remaining	47	40,0	33,0	25,5	19,5	12,5	12,5	5,5	0,5
					ideal rem.	47	40,0	33,0	25,0	19,0	11,0	11,0	3,0	0,0